## Business Plan
Firefighters' Pensions England Scheme Advisory Board - Business Plan
2025-06-01
Introduction
This is the Business Plan for the Firefighters' Pensions England Scheme Advisory Board. The Business Plan is an important document which sets out the aims and objectives of the Board over the coming year, its core work and how the objectives will be achieved. The Firefighters Pension Scheme (England) Scheme Advisory Board (the “Board”) is a body set up under Section 7 of the Public Service Pensions Act 2013 and The Firefighters’ Pension Scheme (Amendment) (Governance) Regulations 2015. The purpose of the Board is to be both reactive and proactive to carry out the following functions: - provide advice in response to a request from the Secretary of State on the desirability of making changes to this scheme and any connected scheme - provide advice to scheme mangers and local pension boards in relation to the effective and efficient administration and management of this scheme and any connected scheme. It will seek to encourage best practice, increase transparency, coordinate technical and standards issues, and build positive relationships with stakeholders and industry bodies – such as the Ministry of Housing, Communities and Local Government (MHCLG), The Pensions Regulator and the Government Actuary’s Department. This business plan has been prepared to be consistent with MHCLG's work plan. The Plan is reviewed annually, and progress monitored at each meeting. New priorities that might arise can be introduced at each meeting and new action identified where progress has not been as expected.
Budget
The Board is required to submit an annual budget to the Secretary of State each year for approval. Once approved the budget for the Board is funded via a statutory levy on Fire and Rescue Authorities, based on a cost per active member of the schemes. The budget for the 2024/25 year was approved at the September 2024 SAB meeting. Actual expenditure over 2024/25 was reviewed in Spring 2025, with a proposed budget for 2025/26 being presented at the 18 June 2025 SAB meeting. Going forward it is proposed that the annual budget will be presented to SAB in June 2025, alongside the review of the business plan.
Training
Training to acquire a sufficient level of knowledge and understanding is an important part of a Board member’s role, and appropriate time should be made to undertake training and development activities. Members should undertake a personal training needs analysis and use this to review their skills, competencies, and knowledge on a regular basis in order that action can be taken to address any gaps. On an annual basis the Board are asked to complete a Training Needs Analysis (TNA), to allow the secretariat to develop a Board training plan.
Risk Management
The board has an established risk register, which is reviewed bi-annually
Issues for attention for the coming year
- Sargeant implementation issues - Matthews implementation issues - Pensions Dashboards - 2024 valuation - assumptions and results - implementation of changes to employee contribution rates from April 2026
Key Tasks and activities
- Agree and monitor business plan - Agree budget for 25/26 - Develop Training and Development amongst board members -
SAB Communications Strategy
To be completed
Date of next review
2026-06-01

## Communication Strategy
Board Communication Strategy
Objectives
- Build trust in the operation and governance of the Board - Improve awareness of how the Scheme operates - Encourage clear, simple communications for members - Provide accessible resources for stakeholders to carry out day-to-day provisions in the Scheme
Key stakeholders / audiences
- Scheme members - Scheme Managers - Scheme Administrators - Local Pension Boards - Fire & Rescue Authorities, including HR and Finance colleagues - Trade unions and employee representatives - Government departments and policymakers, including MHCLG and GAD
Communication channels
- Key policy documents including: - Code of Practice - Conflicts of Interest - Knowledge and understanding - Risk register - Budget Setting - Board website (FPSBoard.org) Operated by LGA. Holds information about the work of the Board and its three committees, as well as useful information and resources for Local Pension Boards. Can be used to share updates and announcements with stakeholders, and share board publications. A restricted area of the website is for Board members only, which hosts meetings papers, advice papers, and other restricted material. - LGA Monthly Bulletins A Board update section is included within each Bulletin, which can be use to communicate to stakeholders. - Annual fire pensions conference Two day conference, hosted by LGA and the Chair of the Board, with several sessions to allow the Board to provide updates to attendees - Annual review An annual report summarising the work of the Board over the previous 12 months, and upcoming areas of focus. - Summary update to Local Pension Board Chairs A summary letter addressed to LPB Chairs following each Board meeting to highlight the key areas of discussion. Encouragement for LPB Chairs to include as part of their LPB agendas. - Local Pension Board forums Informal meeting faciliatated by LGA, where LPB Chairs are invited to raise any area of firefighters' pensions as needed. The Board Chair and LPB Effectiveness Committee Chair attend. - Ad-hoc emails Operated by LGA. - Member website (FPSMember.org) Operated by LGA, to provide members with the latest news & announcements, and information about benefits in the Scheme, including Sergeant and Matthews Remedies, providing answers to FAQs and where to go for further information - LGA website (FPSRegs.org) Not strictly a Board communication channel, but included for completeness. Operated by LGA. Holds all resources relating to the administration of the Firefighters’ Pension Schemes and provide Fire & Rescue Authorities and administrators with tools and guidance to provide an efficient and effective service to their members. Access not generally provided to Board members. - FPS Coffee Mornings Not strictly a Board communication channel, but included for completeness. Facilitated by LGA for FPS practitioners and managers. Informal sessions allow practitioners to catch up with colleagues and hear a brief update on FPS issues from the LGA Bluelight team.
Summary of SAB communications, and communication channels used
1. Agendas and Minutes of Board and committee meetings - on Board website 2. Information about the Board, including membership, meeting attendance, and polices/documents - on Board website 3. Board communications, responses to public consultations, reports of Board surveys - on Board website 4. Distribution of resources for LPBs - on Board website 5. Ad-hoc updates - via email, LGA bulletins 6. Summary of work carried out - Chair's update at Annual Fire Pensions Conference and annual report
Key areas for the coming 12 months
1. Support members with implementation of Sergeant and Matthews Remedies 2. Provide support for implementation of revised employee contribution rates in Q4 2025/Q1 2026 (date TBC by MHCLG) 3. Support the communication of 2024 valuation results, and the impact on employer contribution rates and any cost-cap implications 4. Finalise policy and approach for sharing of confidential information (e.g. redacted public-facing minutes, administrator tools such as Matthews calculator, online 'log' of all third-party advice received etc). 5. Develop Equality and Diversity and Inclusion policy 6. Develop new and improved member website 7. Encourage the sector to enhance digital offering through administrators software providers (member self-service) 8. Agree formal communication channels with Local Pension Boards to include formal Board inbox facilitated by LGA 9. Facilitate a face to face LPB Chairs forum on Day one of the Annual Conference

## Planner
Firefighters' Pensions England Scheme Advisory Board - Business Plan | [15 empty] | Key:
Plan Duration
Actual Start
% Complete
Month Highlight: | 2025-09-01 |  | 4 | [13 empty] | Actual (beyond plan)
Start Date | 2025-06-01 | [15 empty] | % Complete (beyond plan)
Task | Category | Planned start | Planned start | Planned duration (months) | Actual start | Actual start | Actual duration (months) | % complete
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
 | time axis 2025-06-01 to 2029-05-01
Board members complete Training Needs Analysis 2025 | Governance | 2025-06-01 | 1 | 1 | 2025-06-01 | 1 | 1 | 0%
2024 valuation - Key assumptions discussions with GAD | Valuation | 2025-06-01 | 1 | 1 | 2025-06-01 | 1 | 1 | 0%
2024 valuation - SAB training | Valuation | 2025-06-01 | 1 | 1 | 2025-06-01 | 1 | 1 | 0%
Board Policy Documents review 2025 | Governance | 2025-06-01 | 1 | 3 | 2025-06-01 | 1 | 3 | 0%
Review and agree SAB communications strategy | Governance | 2025-06-01 | 1 | 4 | 2025-06-01 | 1 | 4 | 0%
Agree business plan | Governance | 2025-06-01 | 1 | 4 | 2025-06-01 | 1 | 4 | 0%
Pensions Dashboard | Project - Dashboard | 2025-06-01 | 1 | 7 | 2025-06-01 | 1 | 7 | 0%
Employee contribution changes | Employee contribution rates | 2025-06-01 | 1 | 10 | 2025-06-01 | 1 | 10 | 0%
Sargeant ongoing implementation | Project - Sargeant | 2025-06-01 | 1 | 10 | 2025-06-01 | 1 | 10 | 0%
Matthews ongoing implementation | Project - Matthews | 2025-06-01 | 1 | 12 | 2025-06-01 | 1 | 12 | 0%
Update FPS Member website | Governance | 2025-06-01 | 1 | 12 | 2025-06-01 | 1 | 12 | 0%
Agree SAB budget 2025/26 | Governance | 2025-07-01 | 2 | 3 | 2025-07-01 | 2 | 3 | 0%
2024 valuation - Assumptions discussions | Valuation | 2025-07-01 | 2 | 6 | 2025-07-01 | 2 | 6 | 0%
LGA Fire Pensions Conference | Event - AGM | 2025-09-01 | 4 | 2 | 2025-09-01 | 4 | 2 | 0%
Review risk register H2 2025 | Governance | 2025-09-01 | 4 | 1 | 2025-09-01 | 4 | 1 | 0%
Review risk register H1 2026 | Governance | 2026-03-01 | 10 | 1 | 2026-03-01 | 10 | 1 | 0%
2024 valuation - Initial Results (employer rate / cost cap outcome) | Valuation | 2026-03-01 | 10 | 3 | 2026-03-01 | 10 | 3 | 0%
Board members complete Training Needs Analysis 2026 | Governance | 2026-03-01 | 10 | 3 | 2026-03-01 | 10 | 3 | 0%
Board Policy Documents review 2026 | Governance | 2026-06-01 | 13 | 3 | 2026-06-01 | 13 | 3 | 0%
Review business plan 2026 | Governance | 2026-06-01 | 13 | 3 | 2026-06-01 | 13 | 3 | 0%
Agree SAB budget 2026/27 | Governance | 2026-07-01 | 14 | 3 | 2026-07-01 | 14 | 3 | 0%
Review risk register H2 2026 | Governance | 2026-09-01 | 16 | 1 | 2026-09-01 | 16 | 1 | 0%
Review risk register H1 2027 | Governance | 2027-03-01 | 22 | 1 | 2027-03-01 | 22 | 1 | 0%
Board members complete Training Needs Analysis 2027 | Governance | 2027-03-01 | 22 | 3 | 2027-03-01 | 22 | 3 | 0%
2024 valuation - Implementation of changes (contributions/benefits) | Valuation | 2027-04-01 | 23 | 1 | 2027-04-01 | 23 | 1 | 0%
2024 valuation - review member contribution tiers | Employee contribution rates | 2027-04-01 | 23 | 9 | 2027-04-01 | 23 | 9 | 0%
Board Policy Documents review 2027 | Governance | 2027-06-01 | 25 | 3 | 2027-06-01 | 25 | 3 | 0%
Review business plan 2027 | Governance | 2027-06-01 | 25 | 3 | 2027-06-01 | 25 | 3 | 0%
Agree SAB budget 2027/28 | Governance | 2027-07-01 | 26 | 3 | 2027-07-01 | 26 | 3 | 0%
Review risk register H2 2027 | Governance | 2027-09-01 | 28 | 1 | 2027-09-01 | 28 | 1 | 0%
Review risk register H1 2028 | Governance | 2028-03-01 | 34 | 1 | 2028-03-01 | 34 | 1 | 0%
Board members complete Training Needs Analysis 2028 | Governance | 2028-03-01 | 34 | 3 | 2028-03-01 | 34 | 3 | 0%
Board Policy Documents review 2028 | Governance | 2028-06-01 | 37 | 3 | 2028-06-01 | 37 | 3 | 0%
Review business plan 2028 | Governance | 2028-06-01 | 37 | 3 | 2028-06-01 | 37 | 3 | 0%
Agree SAB budget 2028/29 | Governance | 2028-07-01 | 38 | 3 | 2028-07-01 | 38 | 3 | 0%
Review risk register H2 2028 | Governance | 2028-09-01 | 40 | 1 | 2028-09-01 | 40 | 1 | 0%
2028 Valuation - data collection | Valuation | 2028-12-01 | 43 | 3 | 2028-12-01 | 43 | 3 | 0%
2028 Valuation - SAB training | Valuation | 2029-03-01 | 46 | 1 | 2029-03-01 | 46 | 1 | 0%
Activity |  |  | #N/A |  | 0 | #N/A | 0 | 0%
Activity |  |  | #N/A |  | 0 | #N/A | 0 | 0%
Activity |  |  | #N/A |  | 0 | #N/A | 0 | 0%
Activity |  |  | #N/A |  | 0 | #N/A | 0 | 0%
Activity |  |  | #N/A |  | 0 | #N/A | 0 | 0%
Category List
Governance
Valuation
Employee contribution rates
Project - Dashboard
Project - Sargeant
Project - Matthews
Event - AGM
Formulas:
Actual start = [Planned start]